## Incident Lists
TPS INCIDENT REPORTING DATABASE 2024
N° | Reported by | Site | Location on site | Date/ Time Occurred | PEAR Class | Sub category | Brief Decription including injury, damage, loss or spill info | Inc Type if injury | If Asset integrity incident (Facility/Pipeline/Structure/Well) | Damaged zone | PSE Tiers (1/2/3/4) | Act Sev | Potl Sev | Investigation Done? | Immediate Causes | Root Causes | CA's Taken | Suggestions/recommendations
1 | A.GHATTASSI | MAIN OFFICE | 2nd floor | 2024-01-02 | Injury/Illness | Injury/Illness | Due to a disease, the cleaning maid hanged on the electrical cables and fell: trip hazard | Medical Treatment Case |  |  |  | 1 | 2 | No | She was in a hurry | Lack of attention due to rush to end work | Basic first aid provided. Informed cleanign lady to pay attention and to not rush, as rushing can only cause accidents and result in further delays. | .Regular health check-ups for staff to ensure they are fit for their duties .Regularly inspect the work environment for potential hazards, including loose cables and other trip hazards.
2 | A.LABYADH | CERCINA | DELTA PLATFORM | 2024-02-09 | Injury/Illness | Injury/Illness | At 11:30, a contracted welder was performing the housekeeping of the working area when he accidentally run an impact wrench. A locking pin installed on the wrench rotated and caused a superficial injury to his right calf. Immediate action was taken to ensure the safety and well-being of the IP. The IP was evacuated from the workplace, and the HSSE technician on-site administered first aid techniques. The wound was thoroughly cleaned, disinfected, and appropriately wrapped. Simultaneously, the on-duty doctor was notified, and he quickly mobilized to the jetty, awaiting the arrival of the IP. Upon arrival at the jetty, the on-duty doctor conducted an initial exploration of the injury and accompanied the IP to KERKENNAH hospital. At the hospital, a detailed examination revealed the extent of the injury, leading to the application of five sutures for proper wound closure. The necessary medical procedures were efficiently carried out to ensure the IP's recovery. | LTI |  |  |  | 3 | 3 | yes | Accidental run of impact wrench | TBD | Stop work for safety stand down Wrench was immediately removed from site ( No more used) | .Ensure an adequate supply of BA rings and GA pins for all Impact Wrenches in TPS. .Provide initiation training / awareness sessions based on the Manufacturer Instructional Manual for Impact Wrench users. .Provide trainings to relevant personnel on LOTO Procedures, Housekeeping and works in process areas. .Include hand-held tools and their manufacturer instructional manuals in risk assessments. Integrate impact wrenches and other hand-held tools into the CMMS for regular maintenance. .Ensure adequate resourcing for each specific task, including qualified job supervision. .Notify the vendor / manufacturer about discrepancies in safety information in the Manufacturer Instruction Manual. .Boost the implementation of a monitoring system for tool purchases and encourage timely registration in the warehouse. .Enhance HSSE considerations throughout the supply chain process. .Strengthen QA/QC processes for purchased tools.
3 | R.RAHALI / H.BEN BEY | CERCINA | CERCINA 7A WO 5 | 2024-03-04 | Asset damage | Asset damage | The breakdown of the EPF 6-cylinder gas generator has led to the shutdown of Cercina 1 ESP. Although the EPF diesel generator continues to power the ESPs of some wells, it is unable to handle the increased temperature resulting from the integration of Cercina 2 well. As a precautionary measure, it was decided to temporarily shut down Cercina 2 well to ensure uninterrupted production from the other wells | Asset Integrity (Tehnical) | Facility | Cer-3 and Cer sth 1 shut-in for about 1.5 hours |  | 1 | 1 |  | Workover team wasn’t aware that this a Gas line. | Lack of coordination between production and Workover | Open the gas valve. | Mark (signal) the valve to avoid error close.
4 | H.JARRAYA | EL AIN | EL AIN 3SD WO 6 | 2024-04-01 | Asset damage | Asset damage | Two Electrical cables in bad shape due to false maneuver and excessive move of forklift on the cable guard protectors | Asset Integrity (Opertaional) | Facility | Electrical cables |  | 1 | 1 |  | False maneuvre of forklift operator in the same place | The area is very limited | Avoid move of forklift on electrical cabels istruct the forklift operator to change the trajectory | Use heavy-duty cable protectors designed to withstand the weight and movement of forklifts. Protect electrical cables by laying them inside cable protective hamp.
5 | I.BEN HAMAD | GUEBIBA STATION &GUEBIBA CLUSTER | GUEBIBA &GUEBIBA CLUSTER | 2024-04-01 | Asset damage | Asset damage | During the previous period, the water cut of Guebiba cluster wells was increased, which caused the rise of flow line temperatures [Gue#2: 241 °F] ; [Gue#9: 230 °F] ; [Gue#10: 240 °F] ; [Gue#14: 228 °F] | Asset Integrity (Design & Operational) | Pipeline | Pipeline expansion | PSE (Tier 3) | 2 | 3 |  | Thermal expansion due to hot fluid temperatures within the pipeline | The maximum operating temperature of the pipeline cannot support the high temperature of the fluid. |  | Select only the well which can be supported by maximum operating temperature of the pipeline Added an expansion loop to reduce the effects of thermal movement. Build a concrete anchor block from both sides to restrain the movement of the pipeline.
6 | R.RAHALI / H.BEN BEY | EL AIN | EL AIN 3SD WO 6 | 2024-04-04 | Asset damage | Asset damage | During the phase of POOH of completion and after unset Packer & POOH 8 joints, we noticed a high increase of overpull to 48 Tons (normal weight is 30 Tons). With presence of Weatherford completion engineer, we working the string up & down with 22 Tons to 59 Tons, sucsseded to release the string and lay down working joint. Try to pull additional joint but get stucked after 4 m. Made several attempts to free the string without success. Secure the well and held meeting with completion engineer of Weatherford to agree on way forward. | Asset Integrity (Technical) | Well | Well | PSE (Tier 3) | 2 | 3 |  | Probably deposits trapped between the Packer and Casing caused a stuck. |  | .Lay down free joint. .Secure the well .Submit an incident report
7 | M. BEN HAMMOUDA | GUEBIBA | El-HAJEB | 2024-05-01 | MEDEVAC | MEDEVAC | At 11:15 the crew chief was informed about the watchman of El Hajeb Site feeling not good ( pain in the rib cage ). Immediately, The Production Foreman and HSSE technician went to El Hajeb Site , founded the Rhemoura civil Protection in Elhajeb site for routine inscpection, assessed the situation, Performed the First aid treatment for the whatcham, Informed TBC and called the Civil protection for MEDEVAC | Meadical Treatment Case |  |  |  | 2 | 2 |  |  |  | Immediately, The Production Foreman and HSSE technician went to El Hajeb Site , founded the Rhemoura civil Protection in Elhajeb site for routine inscpection, assessed the situation, Performed the First aid treatment for the whatcham, Informed TBC and called the Civil protection for MEDEVAC
8 | W.AGREBI | TANK BATTERY | TANK BATTERY | 2024-05-07 | Asset damage | Asset damage | During a routine survey for the Tank Battery field assets, a slight oily water leak was detetected on the level of flange bottom on the Pig receiver post SDV of the 8 inch Rehmoura TB pipeline entry in the TB field. | Asset Integrity (Technical) | Pipeline | The Ring or flange face could be damaged | PSE (Tier 2) | 1 | 1 |  | A doubt of corrosion in the internal part of the Ring groove or a damge in the Ring itself. | To be defined |  | Plan for a deeper diagnosis and convenient repair with a dedicated reparation procedure.
9 | R.BEN DJEMAA | GUEBIBA | GUEBIBA 7 | 2024-05-19 | Security | Security | During an operator’s visit to Gue#7, he noticed the absence of the watchman guard at 1:15 p.m. and when we contact him by telephone, he showed up at el-hajeb to purchase bread | Security |  |  |  | 1 | 2 |  |  |  | Replace the watchman | .Provide additional training to the watchman on the importance of their role and responsibilities .Establish a clear protocol for communication if the watchman needs to leave their post for any reason.
10 | UNREPORTED | GUEBIBA | EL-HAJEB | JUNE | Process Safety | Process Safety | Oil leak coming out from El-Hajeb 7 wellhead. Action to shut in the well was taken and decision will be made to identify the way forward | Asset Integrity (Technical) | Well | Well | PSE (Tier 2) | 1 | 3
11 | M.DAOUES | CERCINA | 6 INCH SEALINE | 2024-06-19 | Process Safety | Process Safety | A fishing boat anchor found attached to the 6” Cercina sea line while repairing the free spans. The pipe presented a small dent but not damaged as per the visual examination and this will be comprehensively checked during the IP campaign. This incident is categorized as HiPo given the potential consequences that could be occurring | Asset Integrity (Technical) | Pipeline | NONE | PSE (Tier 3) | 1 | 6 |  | The existence of the free Span which could be increased due to high current frequency as per the metology. This area is known by frequent fishing activity. | A fishing boat Crew layed the anchor to the seabed for normal fishing activity near the sealine location. By current activity, this anchor was attached to the sealine due to the free span which this area presents. While fisherman tried to pull back the anchor after finishing his job, he couldn't succes in this removal operation; in fact the anchor was sticking hardly to the pipe wall, hence he cutted the anchor wire above the sea level (approximately 3 meters) and left the anchor hanged on the pipe. | Free the pipe portion from the anchor. Assess visually the pipe portion status further to this incident. Repair the free span. The pipe is presenting a small dent but not damaged as per the visual examination, however further to the next IP campaign (with geometric tool) we will check the extent of this dent as well as status of this exact location according to the GPS coordinates. Increase the Free span survey frequency and plan the repair, if any, as soon as possible accordingly.
12 | F.HFAIADH | CERCINA | DELTA PLATFORM | 2024-07-03 | Process Safety | Process Safety | After shift handover, the incoming crew was performing a routine tour when oily water droplets were detected from the 3" pipe linking the manifold to the V02 separator, through which CER#2 production was routed. The team immediately switched the production of CER#2 to V01 separator, isolated the leaking spool (length 6 m), and stopped the leak. The crew chief informed the control room operator, who notified the concerned persons as per the ERP. A survey was performed by boat to check for any sea pollution, and no spill was detected at sea. The site foreman was mobilized immediately to assess the situation with the team and determine if additional measures were required. The construction team is preparing a new spool to replace the damaged one. Scaffolding will be installed to facilitate the replacement. A visual inspection revealed that the puncture was located between the pipe and the metallic support, indicating that the likely cause of the failure was external galvanic corrosion. | Asset Integrity (Technical) | Pipeline |  | PSE (Tier 2) | 1 | 3 |  | Galvanic Corrosion due to inadequate insulation between the pipe and the support | TBD | Isolation of the leaking spool Preparing a new spool for replacement Check the insulation between pipes and related supports and proceed with adequate insulation.
13 | C.TAKTAK | TANK BATTERY | TANK BATTERY | 2024-07-18 | Security | Security | 03 immigrants from sub-Saharan Africa entered the Tank Battery site through the parking lot gate, which was open during the shift change. Spotted and pursued by the National Guard, they took refuge in our premises. The site security guards apprehended them and alerted the control room, the National Guard, and the military personnel. The National Guard arrived quickly and took custody of the three individuals. The incident caused no harm to people or property | Security | [9 empty] | Repair Tank Battery gate, particulary the automation system
14 | H.BEN BEY | GUEBIBA | GUEBIBA#14 WO MAIN GATE | 2024-09-06 | Asset damage | Asset damage | It happened when the CTF Rig 01 Cabot truck was almost exiting Guebiba 14 WO site towards Guebiba 3 WO site, collided the door and resulted in partial damage of the left side gate and TPS car parked in the vicinity. Fortunately, no one was exposed to the risk of injury at the time of the incident | Asset Integrity |  |  |  | 1 | 3 |  | Only one banksman Poor supervision |  | -Stop work '-Stand out time for safety during 30 mn in both site Gue#14 and Gue#3 '-Made a temporary gate to secure the well site during the night and initiate process with production to make a new gate
15 |  | EL AIN | TPS pipe | 2024-10-11 | Near Miss | Near Miss | some excavation works performed by SONED the public water company where TPS pipe passes around 300 m from Ain Site, and no prior notification been addressed by SONED | Near Miss | Pipeline | NONE | PSE (Tier 3) | 0 | 2 |  |  |  |  | Official letter should be issued and submitted to SONEDE emphasizing this issue and highlighting what can be resulted if things become worsen. Attach all pipeline assets of TPS to the letter. This can also be generalized with the other potential public companies such as STEG. Request the advanced center of fire brigade to enhance the level of surveillance at the hot spots.
16 |  | CERCINA | Cercina sealine | 2024-10-13 | Security | Security | Security Incident near Cercina sealine: A partially submerged boat was discovered during the routine inspection of the sealine. Authorities were informed by TPS Security Coordinator and they stated that will take the necessary actions. NTR on people, asset, environment or reputation. | Security
17 |  | GUEBIBA BASE | Load out Station | 2024-11-08 |  |  | At 11:30, during the start of water loading operations to tanker Cistern No. 117333, the pumper identified a leak from the tanker and immediately informed the crew chief. The crew chief coordinated with the onsite team and took swift action to manage the situation by isolating the truck in a designated safe area and placing a retention tray under the leak to prevent soil contamination. The crew chief then mobilized a vacuum truck from TEPS Company (TPS contractor accredited to transport contaminated water) to empty the tanker and ensure it was free from residual water. Approximately 2 to 3 liters of produced water were spilled from the tanker. |  |  |  |  | 1 | 2 |  | Internal corrosion of the the truck tanker | Lack of preventive inspection of the Contractor's tanker | Isolated the truck in a designated safe area. Placed a retention tray under the leak to prevent soil contamination. Transferred the loaded quantity of produced water from the truck tanker using TEPS vacuum truck, ensuring the tank was fully emptied and free of residual water. | Invite the contractor to an SQM. Conduct a third-party inspection of all tankers due to the recurrence of similar incidents. Ensure that a truck tanker equipped with a pump is on standby for immediate availability if needed, as recommended during the drill. Select the adequate training for onsite personnel for intervention in case of leak from truck tanker
18 | A.KARRA | GUEBIBA BASE | Load out Station | 2024-12-03 |  |  | When start water loading by truck using cistern n° 116201 at 20:50 the pumper detect a leak from tanker. Immediately inform the crew chief and proceed to discharge 45 bbls water process by TEPS Company . |  |  |  |  | 1 | 3
Note on F6: JPVDE: Env Sec Injury/Illness Asset Damage Transportation
Note on I6: JPVDE: FAC MTC RWC LTI FAT HiPo N/A